## Sheet1
Define Course Objectives and Target Audience | Conduct market research to identify the demand.
Define Course Objectives and Target Audience | Define the learning objectives and target audience for the course.
Create Course Outline | Develop a detailed outline of the course content and structure.
Create Course Outline | Include modules, topics, and estimated duration for each.
Design Course Materials | Develop slides, handouts, or any necessary materials for the course.
Design Course Materials | Ensure alignment with the course objectives.
Select and Prepare Instructors | Identify and invite qualified instructors for the course.
Select and Prepare Instructors | Provide them with necessary information and resources.
Set Up Registration System | Choose or set up a platform for course registration.
Set Up Registration System | Ensure a user-friendly registration process.
Marketing and Promotion | Develop a marketing plan to promote the course.
Marketing and Promotion | Utilize various channels like social media, email, or university announcements.
Logistics and Technical Setup | Arrange the necessary technical infrastructure for online or offline delivery.
Logistics and Technical Setup | Ensure compatibility with participants' devices.
Participant Enrollment | Monitor and manage participant enrollment.
Participant Enrollment | Address any issues related to enrollment.
Sprint Review and Adaptation | Review progress and adapt plans based on feedback.
Sprint Review and Adaptation | Identify and address any issues or changes needed.
Conduct Pilot Sessions | Conduct a pilot session to gather feedback.
Conduct Pilot Sessions | Make necessary adjustments based on the pilot results.
Finalize Course Schedule | Confirm the schedule for the course sessions.
Finalize Course Schedule | Communicate the schedule to participants and instructors.
Launch and Delivery | Execute the launch of the course.
Launch and Delivery | Monitor and support the delivery of the course sessions.
Facilitates the Scrum process and ensures adherence to Agile principles.
Helps the team overcome challenges and impediments.
Promotes a collaborative and self-organizing team environment.
Acts as a coach for the team.
Development Team:
Cross-functional group responsible for delivering the product.
Comprised of individuals with different skills necessary for project completion.
Self-organizing and responsible for managing their work during a sprint.
Stakeholders:
Individuals or groups with an interest or concern in the project.
Provide feedback and have input on the product.

## Sheet2
Feature | Backlog | Sprint#1 | Sprint#2
Define Course Objectives and Target Audience | Conduct market research to identify the demand.
Define Course Objectives and Target Audience | Define the learning objectives and target audience for the course.
Create Course Outline | Develop a detailed outline of the course content and structure.
Create Course Outline | Include modules, topics, and estimated duration for each.
Design Course Materials | Develop slides, handouts, or any necessary materials for the course.
Design Course Materials | Ensure alignment with the course objectives.
Select and Prepare Instructors | Identify and invite qualified instructors for the course.
Select and Prepare Instructors | Provide them with necessary information and resources.
Set Up Registration System | Choose or set up a platform for course registration.
Set Up Registration System | Ensure a user-friendly registration process.
Marketing and Promotion | Develop a marketing plan to promote the course.
Marketing and Promotion | Utilize various channels like social media, email, or university announcements.
Logistics and Technical Setup | Arrange the necessary technical infrastructure for online or offline delivery.
Logistics and Technical Setup | Ensure compatibility with participants' devices.
Participant Enrollment | Monitor and manage participant enrollment.
Participant Enrollment | Address any issues related to enrollment.
Sprint Review and Adaptation | Review progress and adapt plans based on feedback.
Sprint Review and Adaptation | Identify and address any issues or changes needed.
Conduct Pilot Sessions | Conduct a pilot session to gather feedback.
Conduct Pilot Sessions | Make necessary adjustments based on the pilot results.
Finalize Course Schedule | Confirm the schedule for the course sessions.
Finalize Course Schedule | Communicate the schedule to participants and instructors.
Launch and Delivery | Execute the launch of the course.
Launch and Delivery | Monitor and support the delivery of the course sessions.